## Table of Contents
Define | Project Charter
RACI Matrix
Process Map
Measure | KJ Analysis
Process Capability (Bagging)
Analysis | C&E Matrix
FMEA
Multi-Vari Analysis
Improve | Pugh Matrix
Design of Experiment (DOE) & Results
Students' Feedback on DOE
Control | Revamped Solution and DOE 2
Breakeven Analysis
Control Plan
Others | Meeting Minutes
Timeline

## Project Charter
| Organisation | SMU Li Ka Shing Library | Lean Six Sigma Team Charter
| Project Name | SMU Library Seat Utilisation | Date & Version | 22/4/2015, V5
| Green Belt Candidates | Jo Lee Xin | Contacts | joxin.lee.2011@business.smu.edu.sg; 9297 3297
|  | Eileen Tan Yi Lin |  | eileen.tan.2012@business.smu.edu.sg; 9236 1993
|  | Lee Shu Wei |  | shuwei.lee.2011@business.smu.edu.sg; 9179 1343
|  | Joshua Lim Thiow Ern |  | telim.2012@business.smu.edu.sg; 9170 7481
|  | Aldred Lau Wen Yang |  | aldred.lau.2012@business.smu.edu.sg; 9178 1198
| Process Owner | Yuyun Wirawati Ishak Vincent Ong | Business Impact ($) | Opportunity cost of $1,240 per semester
| Executive Champion |  | Business Unit
| Start Date | 2015-01-07 | Target Completion | 2015-04-23
| Element | Description | Team Charter
1. | Process Definition | The work process in which opportunity exists. | User: Student visits the library. If he cannot find a seat, he has to leave the library and look for alternative study spaces.
Library Staff: When seat hogging happens, library receives a complaint (email/face-to-face). Library staff addresses the complaint and proceeds to take action. At regular intervals, a library staff will patrol around Levels 2,3,4 and distribute 'hogging slips'. The hogger is expected to remove his belonging (or be at his seat) within 30 minutes. 30 minutes later, a library staff will do another round of patrol to check if seats are still hogged. If it is, items are stored in a trashbag and deposited at the security. To claim their items back, students have to visit the security. This process is done twice a day.
2. | Business Case | Describe the opportunity as it relates to business goals. | Instances of students finding alternatives in face of the lack of seats is misaligned with the library's mission of providing adequate learning space for the SMU community. Complaints arising from the lack of seats increase required manpower to address and take action. In addition, current solution of distributing 'hogging slips' and removing of belongings greatly increases unnecessary required manpower, and further generates more complaints. As a result, both library space and manpower are not utilised effectively to improve the core service the library seeks to provide.
3. | Problem Statement | State the significant issue the team wants to improve. Where is the pain? | From Weeks 11-14 of the academic semester, the Library sees a surge in the percentage of hogged seats to up to 31% of its capacity, which diverts manpower from its main operations to deal with both the problem and the complaints from users that ensue.
4. | Project Objective | What improvement is targeted and what will be the impact? | Y: Library Seat Utilisation |  | Baseline | Goal | Entitlement | Units
|  | Quality metrics (Detailed calculations shown below): | Y1: Percentage of Hogged Seats to Total Seat Capacity |  | 31% | <20% | 0% | -
|  |  | Y2: Number of Complaints Related to Seat Hogging |  | 13 | 6 | 0 | Per Semester
|  |  | Y3: Number of Man Hours Taken to Clear Hogged Seats |  | 100 hours | 50 hours | 0 hour | Per Semester
|  | Counter metric: | User Satisfaction (Measured by SMU Library Quality Survey "Library as Place") |  | 7.3 | ≥7.3 | 10 | -
|  |  | Number of complaints related to control measure |  | N.A | Minimize | 0 | -
|  |  | Financial Cost |  | 2,000 (100h X $20) | Minimize | 0 | $
|  | Productivity Improvement: | Manhours
|  | Financial Benefits: | Cost of manhours library can put to better use
5. | Benefit Impact (in 2015 Dollars) | What is the improvement in business performance (Operating Income, Working Capital) anticipated and when? (Detailed calculations shown below) | Cost of implementation will breakeven after 3.5 semesters. The library will see a cost saving of $1,240 per semester. Refer to 'Breakeven Analysis' tab for detailed calculations.
6. | Scope & Boundaries | Describe the project's scope and boundaries. Describe what is in and outside the scope. | In scope: - % of hogged seats to total seat capacity in Level 2-4. - Complaints related to seat hogging Outside scope: - Project rooms and post graduate spaces (level 5) - Complaints due to capacity constraints (i.e. library too small)
7. | Schedule & Milestones | List the key milestone activities with dates. Consider DMAIC. | DMAIC Phases | Due Date | Activity
|  |  | Define | 2015-01-14 | Intial Project Chartering
|  |  |  | 2015-01-21 | Initial Process Mapping
|  |  | Measure | 2015-01-21 | Intial KJ analysis with client
|  |  |  | 2015-01-28 | Refine Process Map and KJ Analysis
|  |  |  | 2015-02-09 | Measurement System Analysis
|  |  | Analyse | 2015-01-28 | Initial C&E Matrix
|  |  |  | 2015-02-16 | Failure Mode and Effects Analysis
|  |  | Improve | 2015-02-25 | Pugh Matrix
|  |  |  | 2015-03-11 | Design of Experiment
|  |  |  | 2015-04-07 | Design of Experiment 2
|  |  | Control | 2015-04-19 | Control Plan
8. | Benefit to company and/or customers | Who are the internal/external customers, what benefit will they see and what are their most critical requirements? | Internal Customers: SMU Students, graduates, faculty Less complaints from library users and more productive manhours for library staff.
9. | Support Required | Will you need any special capabilities, hardware, etc? | Seat hogging data, manpower for observation & experiments & implementation, surveys, booking systems, gantries
10. | Core Team Members | Who are the full-time members? Who is the Process Owner? | Full time Members: Yuyun (Process Owner) and Vincent (Manager In Charge of handling complaints)

## RACI Matrix
Colour Chart on Roles SMU Team Members SMU Faculty Staff SMU Library Team Members |  | Shu Wei | Jo | Eileen | Joshua | Aldred | Prof Adel | Yuyun | Vincent | [6 empty] | Shu Wei | Jo | Eileen | Joshua | Aldred | Prof Adel | Yuyun | Vincent | 0 | 0 | 0 | 0 | 0 | 0
Process Step: Relationship Code: R=Responsible(4), A=Accountable(3), C=Consultation(2), I=Informed(1)
Activity | Period
Schedule next meeting, Email Prof and Library | Week 3-13 | I | R | I | I | I
Meeting Chair | Week 3 | R | I | I | I | I | [9 empty] | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 4 | I | R | I | I | I | [9 empty] | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 5 | I | I | R | I | I | [9 empty] | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 6 | I | I | I | R | I | [9 empty] | 1 | 1 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 7 | I | I | I | I | R | [9 empty] | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 8 | R | I | I | I | I | [9 empty] | 4 | 1 |  | 1 | 1
| Week 9 | I | R | I | I | I | [10 empty] | 4 |  | 1 | 1
| Week 10 | I | I | R | I | I | [10 empty] | 1 |  | 1
| Week 11 | I | I | I | R | I | [12 empty] | 4
| Week 12 | I | I | I | I | R
| Week 13 | R | I | I | I | I
Meeting Vice-chair | Week 3 | I | R | I | I | I | [9 empty] | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 4 | I | I | I | I | R | [9 empty] | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 5 | R | I | I | I | I | [9 empty] | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 6 | I | R | I | I | I | [9 empty] | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 7 | I | I | R | I | I | [9 empty] | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 8 | I | I | I | R | I
| Week 9 | I | I | I | I | R | [9 empty] | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 10 | R | I | I | I | I | [9 empty] | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 11 | I | R | I | I | I | [9 empty] | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 12 | I | I | R | I | I | [9 empty] | 1 | 1 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Week 13 | I | I | I | R | I | [9 empty] | 1 | 1 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meeting Minutes | Week 3 | I | R | I | I | I | I | I | I
| Week 4 | I | R | I | I | I | I | I | I | [6 empty] | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 5 | I | I | I | R | I | I | I | I | [6 empty] | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 6 | I | I | R | I | I | I | I | I | [6 empty] | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 7 | I | R | I | I | I | I | I | I | [6 empty] | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 8 | I | I | I | I | R | I | I | I | [6 empty] | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 9 | I | I | I | R | I | I | I | I
| Week 10 | I | R | I | I | I | I | I | I | [6 empty] | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 11 | I | I | R | I | I | I | I | I | [6 empty] | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 12 | R | I | I | I | I | I | I | I | [6 empty] | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 13 | I | I | I | I | R | I | I | I | [6 empty] | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Project Workbook Update and Submission | Week 3 | I | I | I | R | I | C | I | I | [6 empty] | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 4 | R | I | I | I | I | C | I | I
| Week 5 | I | R | I | I | I | C | I | I | [6 empty] | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 6 | I | I | I | I | R | C | I | I | [6 empty] | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 7 | R | I | I | I | I | C | I | I | [6 empty] | 4 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 8 | I | I | R | I | I | C | I | I | [6 empty] | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 9 | R | I | I | I | I | C | I | I | [6 empty] | 4 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 10 | I | I | I | R | I | C | I | I
| Week 11 | I | I | I | I | R | C | I | I | [6 empty] | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 12 | I | R | I | I | I | C | I | I | [6 empty] | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Week 13 | I | I | R | I | I | C | I | I | [6 empty] | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  | 55 | 66 | 54 | 52 | 56 | 27 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 66 | 54 | 52 | 56 | 27 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rating |  | Instructions - Just enter the appropriate letter RACI and the color coding is automatic
A |  | 3 |  | The totals on the bottom are based on the scoring rating that is to the left
C |  | 2 |  | Formulas are hidden in Columns Q - AD
I |  | 1
R |  | 4

## Process Map
Process Map
INPUT | OUTPUT
Assignments Free time Projects Food Bag Valuables Notes | Student ready to look for seat
Empty adjacent seats Seats with power points Quiet corner Seat with window view Overnight hogged seat | Person-occupied seat Bag-occupied seat Empty seat
Empty adjacent seats Ideal seat location | Spread belongings Charging electronics Bag occupied adjacent seat(s)
Mealtime Lesson time Project meetings time Gym/training time Consultation time Toilet break Phone call Smoke break | Unattended belongings Hogged seat Empty seat
Other students looking for seats Hogged seats Occupied seats Unattended belongings | Student unable to find seat goes home Frustrated student who cannot find seat
Suggestion board Email system | Suggestion slips with seat hog complaint Complaint Email Frustrated Librarian
Librarian on duty Complaint email Filled suggestion slips with seat hog complaint | Respond time Email reply
Librarians on patrol | Patrol time Cautious surrounding students
Warning slips | Marked hogged seats
Librarians on patrol | Patrol time
Librarians on duty Prolonged hogged seats Trash bag Camera | Bagging time Bagged belongings Photo of belongings Tired and frustrated librarians Cleared seat
Librarians on duty Security desk Security guard | Deposited belongings
Finished out-of-library activity Unfinished work Unattended belongings | Seat no longer occupied by own belongings Upset student from loss of seat
Bagged belongings | Collection processing time Reprimanding time
Student looks for seat
Student occupies seat
Student leaves seat
Student returns to seat
Student walks through library entrance
Other student finds seat hogged
Student complains
Librarian addresses complaint
Round 1 of patrol around library
Place slips
Round 2 Patrol (30 mins later)
Bag belongings
Deposit at security desk
Collection of belongings

## KJ Analysis
Why do students hog seats?
1. Need for permanent space
Students are afraid of not having a seat
Students want to secure a seat as there are many people in the library
Students intend to return to the library after their group meetings
Library gets very packed during peak hours
Students feels attached to the library as a study haven.
Students want to secure their favourite spot for studying
They need a space to study and complete their revision for the day
2. No hassle to students
Students do not have to make prior booking if they want to use the library
Students use the library to store their belongings
Students without lockers have no place to store their belongings temporarily
Students know that no one (besides library staff) can displace their items should they store them in the library
15 points
3 points
Students do not have situational awareness
Some international students do not have the habit of only occupying the space they need
Some students are oblivious that others have difficulty finding a space to sit.
6 points
1 point
Students want to save a seat for a friend who is joining later
4 points
Some students feel that they are entitled to any amount of space since it is paid for in their school fees
0 point
1 point

## Process Capability (Bagging)
Process Capability (Bagging)
Both processes (Control Level 3 and Bagging Level 4) are in control
  Control:
    Cp 0.36 > Cpk 0.19
    Pp 0.43 > Pp 0.23
  Bagging:
    Cp 0.47 > Cpk 0.36
    Pp 0.48 > Pp 0.36
The mean of the control is 14.65%, as compared to the bagging process mean of 12.41%. The bagging process reduced the % of hogged seats by 2.24%
Bagging helps to control the spread
  Cpk (Bagging) 0.36 > Cpk ( Control) 0.19
However, both processes are off target and not within the customer specification limit of 0% to 20%

## C&E Matrix
Library seats utilisation (seat hogging) |  | Rating of Impact on Big Y | 2 | 0 | 10 | 0 | 6 | 2 | 10 | 10 | 10 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 4 | 7 | 8 | 0 | 0 | 0 | 0 | 10 | 0 | 1 | 1 | 5
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Student ready to look for seat | Person-occupied seat | Bag-occupied seat | Empty seat | Spread belongings | Charging electronics | Bag occupied adjacent seat(s) | Unattended belongings | Hogged seat | Student unable to find seat goes home | Frustrated student who cannot find seat | Suggestion slips with seat hog complaint | Complaint Email | Frustrated Librarian | Respond time | Email reply | Patrol time | Cautious surrounding students | Marked hogged seats | Bagging time | Bagged belongings | Photo of belongings | Tired and frustrated librarians | Cleared seat | Deposited belongings | Upset student from loss of seat | Collection processing time | Reprimanding time | Total
| Process Step | Process Input
48 |  | Students use the library to store their belongings | 9 | 0 | 9 | 0 | 9 | 1 | 1 | 9 | 9 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386
50 |  | Students want to save a seat for a friend | 9 | 3 | 3 | 0 | 9 | 0 | 9 | 3 | 9 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323
46 |  | Students are afraid of not having a seat | 0 | 3 | 9 | 0 | 3 | 0 | 3 | 9 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318
5 | Student walks through library entrance | Bag | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312
26 | Other student finds seat hogged | Unattended belongings | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 9 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 9 | 0 | 1 | 0 | 295
15 | Student leaves seat | Mealtime | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
16 | Student leaves seat | Lesson time | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
17 | Student leaves seat | Project meetings time | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
18 | Student leaves seat | Gym/training time | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
19 | Student leaves seat | Consultation time | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
32 | Round 1 of patrol around library | Librarians on patrol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 3 | 9 | 0 | 0 | 0 | 0 | 261
24 | Other student finds seat hogged | Hogged seats | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 3 | 3 | 9 | 1 | 1 | 3 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 9 | 0 | 9 | 9 | 252
8 | Student looks for seat | Empty adjacent seats | 0 | 0 | 3 | 9 | 9 | 0 | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234
51 |  | Some students feel they are entitled to any amount of space | 1 | 9 | 9 | 0 | 9 | 0 | 3 | 1 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219
12 | Student looks for seat | Overnight hogged seat | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 9 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218
52 |  | Students do not have situational awareness | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207
3 | Student walks through library entrance | Projects | 9 | 3 | 3 | 0 | 1 | 1 | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206
45 | Collection of belongings | Bagged belongings | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 1 | 0 | 9 | 9 | 3 | 3 | 9 | 204
47 |  | Students feel attached to the library as a study haven | 9 | 3 | 9 | 0 | 3 | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202
20 | Student leaves seat | Toilet break | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180
21 | Student leaves seat | Phone call | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180
22 | Student leaves seat | Smoke break | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180
33 | Place slips | Warning slips | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 171
4 | Student walks through library entrance | Food | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106
7 | Student walks through library entrance | Notes | 9 | 0 | 0 | 0 | 3 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106
9 | Student looks for seat | Seats with power points | 0 | 3 | 3 | 0 | 0 | 9 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78
49 |  | Students do not have to make a prior booking | 3 | 3 | 3 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72
14 | Student occupies seat | Ideal seat location | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
30 | Librarian addresses complaint | Complaint email | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
41 | Deposit at security desk | Security guard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 9 | 46
28 | Student complains | Email system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
31 | Librarian addresses complaint | Filled suggestion slips with seat hog complaint | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
37 | Bag belongings | Trash bag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 30
27 | Student complains | Suggestion board | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
6 | Student walks through library entrance | Valuables | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
43 | Student returns to seat | Unfinished work | 3 | 0 | 0 | 9 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
1 | Student walks through library entrance | Assignments | 0 | 3 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
2 | Student walks through library entrance | Free time | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
23 | Other student finds seat hogged | Other students looking for seats | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
40 | Deposit at security desk | Security desk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0 | 1
10 | Student looks for seat | Quiet corner | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Student looks for seat | Seat with window view | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Other student finds seat hogged | Occupied seats | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Librarian addresses complaint | Librarian on duty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Bag belongings | Camera | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Student returns to seat | Finished out-of-library activity | 0 | 9 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 140 | 0 | 1490 | 0 | 408 | 30 | 460 | 1480 | 1270 | 0 | 0 | 84 | 125 | 0 | 0 | 0 | 104 | 189 | 320 | 0 | 0 | 0 | 0 | 210 | 0 | 3 | 15 | 135
Cause & Effect Matrix
Cause and Effect (C&E) Matrix
To narrow down the most influential factors (Xs) contributing to seat hogging (Y), a C&E Matrix was done. All possible input factors (Xs) derived from the process map and KJ analysis were rated on their ability to influence the multiple outputs (y) of the seat hogging process. Each individual output (y) is rated (on a scale of 0 to 10) on their impact on seat hogging (Y). Subsequently, the relationship between each input (X) and each output (y) was analysed and quantified. Strong cause-effect relationships are scored 9, moderate relationships are scored 3, weak relationships are scored 1, and having no relationship translates to a score of 0. Finally, the weighted score for each row is calculated. Factors (Xs) were ranked from the highest to lowest score.
The chart below shows the top causes identified using the C&E Matrix:
1. To store belongings
2. To reserve seats for friends
3. Fear of not having a seat
4. Bag (close by the user)
5. Unattended belongings
6. Out-of-library activities (Meals, Lessons, Project meetings, Training, Consultation)

## FMEA
Process or Product Name: | Seat Utilization in SMU Library | [5 empty] | Prepared by: MPI Student Team |  |  | Page 1 of 1
Responsible: | SMU Library | [5 empty] | FMEA Date (Orig) 16 Feb 2015 (Rev) 8 March 2015
Process Step | Key Process Input | Potential Failure Mode | Potential Failure Effects | SEV | Potential Causes | OCC | Current Controls | DET | RPN | Actions Recommended | Resp. | Actions Taken | SEV | OCC | DET | RPN
What is the process step | What is the Key Process Input? | In what ways does the Key Input go wrong? | What is the impact on the Key Output Variables (Customer Requirements) or internal requirements? | How Severe is the effect to the cusotmer? | What causes the Key Input to go wrong? | How often does cause or FM occur? | What are the existing controls and procedures (inspection and test) that prevent either the cause or the Failure Mode? Should include an SOP number. | How well can you detect cause or FM? |  | What are the actions for reducing the occurrance of the Cause, or improving detection? Should have actions only on high RPN's or easy fixes. | Whose Responsible for the recommended action? | What are the completed actions taken with the recalculated RPN? Be sure to include completion month/year
| Students are afraid of not having a seat | Fear makes student want to reserve a seat | Hogged Seat | 10 | Fear | 10 | None | 10 | 1000 | Expanding library | SMU Management |  | 10 | 10 | 10 | 1000
[10 empty] | Increasing number of seats (no change in library size) | SMU Library |  | 10 | 10 | 10 | 1000
[10 empty] | Seat booking system | Office of Facilities Management |  | 10 | 10 | 10 | 1000
Other student finds seat hogged | Unattended belongings | When belongings are left intentionally to reserve the seat | Hogged Seat | 10 | Selfish and inconsiderate students | 10 | None | 10 | 1000 | Education | SMUSA |  | 10 | 10 | 10 | 1000
[10 empty] | Blacklisting frequent hoggers to deter them from hogging again | SMU Library |  | 10 | 10 | 10 | 1000
[10 empty] | Fine students (e-dollars) | BOSS |  | 10 | 10 | 10 | 1000
[10 empty] | Librarian watch station | SMU Library |  | 10 | 10 | 10 | 1000
Student leaves seat | Out-of-library activity | When students leave their belongings at the seats | Hogged Seat | 10 | Mealtime | 10 | None | 10 | 1000 | Bag drop | SMU Library |  | 10 | 10 | 10 | 1000
[10 empty] | Seat booking system with limited hours | Office of Facilities Management |  | 10 | 10 | 10 | 1000
Student walks through library entrance | Bag | Bag is placed on seat without student | Hogged Seat | 10 | Student wants bag to be at arms' reach | 9 | None | 10 | 900 | Bag hooks under the table | Office of Facilities Management |  | 10 | 9 | 10 | 900
Other student finds seat hogged | Unattended belongings | When belongings left behind due to carelessness give perception of occupied seat | Hogged Seat | 10 | Students do not feel comfortable removing other people's belongings | 9 | None | 10 | 900 | Appoint student body to clear unattended belongings on a regular basis (SMUSA) | SMU Library |  | 10 | 9 | 10 | 900
| Students want to save a seat for a friend | Reserved seat can be utilised by another student | Hogged Seat | 10 | Students like to study with friends | 8 | None | 10 | 800 | Provide spare chairs with tables | Office of Facilities Management |  | 10 | 8 | 10 | 800
| Students use the library to store their belongings | Belongings used to occupy seat | Hogged Seat | 10 | Student take advantage of the library's safety | 8 | Posters, emails (prevent) | 8 | 640 | Bag drop | SMU Library |  | 10 | 8 | 8 | 640
Student leaves seat | Out-of-library activity | When students leave their belongings at the seats | Hogged Seat | 10 | Lesson time | 6 | None | 10 | 600 | Library bag removal alert | SMU Library
Other student finds seat hogged | Unattended belongings | When belongings left behind due to carelessness give perception of occupied seat | Hogged Seat | 10 | Careless students | 5 | None | 10 | 500
Student leaves seat | Out-of-library activity | When students leave their belongings at the seats | Hogged Seat | 10 | Project meetings time | 4 | None | 10 | 400
Student leaves seat | Out-of-library activity | When students leave their belongings at the seats | Hogged Seat | 10 | Consultation time | 4 | None | 10 | 400
| Students use the library to store their belongings | Belongings used to occupy seat | Hogged Seat | 10 | Student take advantage of the library's safety | 8 | Patrols, warning slips, bagging | 4 | 320
Student walks through library entrance | Bag | Bag is placed on seat without student | Hogged Seat | 10 | Bag is very expensive | 2 | None | 10 | 200
Student leaves seat | Out-of-library activity | When students leave their belongings at the seats | Hogged Seat | 10 | Gym/training time | 1 | None | 10 | 100
Student walks through library entrance | Bag | Bag is placed on seat without student | Hogged Seat | 10 | Floor is dirty | 5 | Cleaning schedules | 1 | 50
Other student finds seat hogged | Unattended belongings | When unattended belongings become a security threat | Safety of students compromised | 10 | Terrorist | 1 | Security guards, gantries and cameras | 9 | 90
SCALE
| SEV | OCC | DET
Rating | Severity of effect | Likelihood of occurrence | Ability of defect
10 | Hogged | Very high | Cannot
9 |  |  | Very remote
8 |  | High | Remote
7 |  |  | Very low
6 |  | Moderate | Low
5 |  |  | Moderate
4 |  |  | Moderately high
3 |  | Low | High
2 |  |  | Very high
1 | Not hogged | Remote | Almost certain
The fish-bone diagram below summarises the failure modes and effects of the main factors (Xs) derived from the C&E Matrix:
Process/Product
Failure Modes and Effects Analysis
(FMEA)
The FMEA was used to identify all possible failures in students’ user journey in the library which could lead to seat hogging. Failures were prioritised according to how severe their consequences are (SEV), how frequently they occur (OCC), and how easily they can be detected (DET). The purpose of the FMEA is to identify actions to eliminate or reduce failures starting from the ones with highest priority. This is also an early conceptual stage of our solution design.
Note on I27: Joshua Lim: No controls hence detection is 10

## Multi-Vari Analysis
Multi-Vari Analysis
To reduce the factors (Xs) to consider when designing our solution, factors of statistically low associations were removed from our consideration in the Multi-Vari analysis.
Due to the intangible nature of most the X variables in this process (i.e. dealing with students' motivations and intentions), it was difficult to measure the Xs by observation. Hence, a survey was conducted with 56 SMU students. In the survey, students were asked to indicate whether they hog seats, and to rate how well the 6 key factors (Xs) identified in our above analysis explain their motivation behind seat hogging. For a full report on the survey results, click the icon below:
Following which, a chi-square analysis was conducted to identify factors (Xs) which have statistically significant associations with seat hogging (Y). Below shows our main findings:
How likely do the following statements explain why you seat hog? (TOP 3)
I want to reserve a seat for my friend
I want to secure my seat while I attend a meeting
I want to secure my seat while I go out for a meal
Out-of-library Activity (Meal)
Out-of-library Activity (Meeting)
Reserve Seat For Friend
Chi- Square Results:
2 out of the 6 factors (Xs) showed strong association:
1. Store belongings
2. Unattended belongings
3. Have bag close by
4. Reserve seat for friend
5. Fear of not having a seat
6. Out-of-library activities (meal, meeting, lesson, training, consultation)

## Pugh Matrix
| Pugh Concept Selection Matrix |  |  | Concept # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  |  | Current "Best in Class" | Concept | Expanding library | Increasing number of seats (no change in library size) | Seat booking system | Education | Blacklisting (name and shame) frequent hoggers to deter them from hogging again | Fine students (e-hours) | Bag drop | Seat booking system with limited hours | Bag hooks under the table | Appoint student body to clear unattended belongings on a regular basis (SMUSA) | Provide spare chairs with tables | Librarian watch station | Library bag removal alert
Author
Criteria | Man-hours used to address hogged seats |  | Datum |  | N | N | P | S | P | P | P | P | S | N | P | S | N
Number of complaints received pertaining to seat hogging | bar: 1 to 13
Monetary cost | bar: 1 to 13
Minimise spillover to external parties | bar: 1 to 13
| Student satisfaction (e.g. complaints regarding policies) |  |  |  | P | P | P | S | N | N | N | P | S | S | P | S | P
| Librarian satisfaction |  |  |  | S | S | P | S | N | N | P | P | S | P | N | N | S
| Ease of execution |  |  |  | N | N | N | S | S | P | N | N | S | P | P | P | P
Inclination of adoption by students | bar: 1 to 13
Safety | bar: 1 to 13
|  |  | Totals | P's | 3 | 3 | 5 | 0 | 2 | 3 | 3 | 5 | 1 | 3 | 5 | 2 | 3
|  |  |  | S's | 2 | 1 | 1 | 9 | 5 | 3 | 1 | 1 | 6 | 4 | 0 | 6 | 5
|  |  |  | N's | 4 | 5 | 3 | 0 | 2 | 3 | 5 | 3 | 2 | 2 | 4 | 1 | 1
Scale |  | "P" = Better Than Datum
"S" = Same As Datum
"N" = Worse Than Datum
Pugh Matrix
The Pugh matrix helps determine which potential solutions are more important or ‘better’ than others. It is used to facilitate a disciplined, team-based process for concept generation and selection with the project team and client. Several concepts are evaluated according to their strengths and weaknesses against a reference concept called the datum (base/original concept- Bagging).This matrix encourages comparison of several different concepts against a base concept, creating stronger concepts and eliminating weaker ones until an optimal concept finally is reached.
These concepts have the highest positive scores and were selected for test using Design of Experiment (DOE):
Concept #3: Seat booking system
Concept #8: Seat booking system with limited hours
Concept #11: Provide spare chairs with tables

## DOE & Results
DOE & Results
Introduction to DOE
After narrowing down the top concepts from the Pugh matrix (#3, #8, #11), we proceeded to design experiments to test the concepts. During Week 11-12 of the semester, two main experiments were conducted, (1) an online booking system and (2) the provision of extra chairs (with flip tables). In the first experiment, students were allowed to book a seat for a maximum of 3h daily. To emulate the existing facility booking system, students go online (http://libcal.smu.edu.sg/booking/l3) to select and book their seats. In the second experiment, extra chairs (with flip tables) were placed around the experimental area for students' usage. Level 3 study area (facing campus green was used as the experimental area (see below). Level 4 study area (facing campus green) was used as the control. Hogging percentage was observed and recorded every 2h from 10am to 8pm.
Booking System Extra chairs (with flip tables)
Results: Process capability of the experiment
All processes (Control Level 4 and Level 3 Booking System and Extra Chairs) are in control
  Control:
    Cp 0.43 > Cpk 0.22
    Pp 0.45 > Pp 0.23
  Booking System:
    Cp 0.33 > Cpk 0.13
    Pp 0.31> Pp 0.13
  Extra Seats
    Cp 0.28 > Cpk -0.18
    Pp 0.28 > Ppk -0.18
The mean of the control is 14.9%, as compared to the booking process mean of 15.9% and extra seats process which is 26.4%. The 2 processes did not improve the seat hogging situation.
However, both processes are off target and not within the customer specification limit of 0% to 20%
Therefore, a survey was further conducted to understand the limitations and problems with the experiment. This is further explained in Students' Feedback.

## Students' Feedback
Students' Feedback on DOE
A survey was conducted to gather feedback from students about the experiments carried out. For a full report, click on the icon below.
Below shows our main findings and the possible implications and solutions:
Conclusions from Survey 2 (Booking System) | Conclusions from Survey 2 (Extra Seats)
Students are not using the booking system because:
1. Students do not plan to study in advance, it is often a spontaneous process
2. Students find it troublesome to book a seat
3. There is a time limit on the number of hours for booking of seats
4. Students prefer individual study spaces
Students are hesistant to ask students to leave a seat which they have booked because:
1. They do not wish to break up a group of students studying together
2. They do not wish to draw unwanted attention when they approach a student to leave a seat
Students are not using the extra seats because:
1. Students find the attached table too small and uncomfortable for prolonged studying
2. Students find the position awkward and draws attention to themselves which make them uncomfortable
Modifications to solution from conclusions of survey:
1. Students only book upon arrival at the library through a booking kiosk (Spontaneous studying addressed)
2. Simplify the seat reservation to a familiar process such as the facility booking system
3. There is no time limit on the number of hours to study
4. Change location to Non-Communal Area
5. Students who are found seat-hogging will be denied booking for next 48h
6. Extra seat proved ineffective. Will not be using.

## Revamped Solution & DOE 2
Revamped Solution and Experiment Design (DOE 2)
1. Ensure Fair Seating
How? Instant seat booking system with gantry control
Where? Level 4 individual study cubicles
2. Promote Graciousness
How? Education and Raise Awareness
- ‘No hogging’ posters around Library
- Regular emailers to remind students not to hog
- Heavier-toned emails during peak study periods
- Use of social media to highlight ugly behaviours
Select seat on booking kiosk with matric card. Booked seat has no time limit.
Using matric card, go through gantry into study area. System registers user inside study area.
To exit temporarily, use matric card to exit gantry. System registers user outside study area.
If user does not return in 30 min, his seat will be freed up on the booking system. Belongings will be cleared and deposited at security desk
To exit permanently, check out of the seat on the booking kiosk.
User will be denied from booking for the next 48 hours. He can use other study areas which does not require booking
Book a seat from librarian stationed outside study area
User exchanges matric card for a tag
To exit temporarily, record exit time with librarian. Collect back matric card while holding on the tag.
If user does not return in 30 min, his seat will be freed up. User has to return the tag in exchange for his belongings at the librarian station
User is denied of booking a seat for the next 48h.
To exit permanently, check out of seat with librarian. Return tag in exchange for matric card.
SOLUTION
EXPERIMENT

## Breakeven Analysis
Breakeven Analysis
Manhour cost | 20
Number of Semesters | 1
Bagging Process
Manhour Used for Bagging Exercise/Sem | 100
Cost of Manhour Used for Bagging Exercise/Sem | 2000
Total Cost | 2000
New Booking System
Implementation Cost One time off | 4000
Maintenance Hours/Sem (peak) | 15
Maintenance Hours/Sem (non peak) | 23
Total Number of Maintenance Hours/Sem | 38
Cost of Maintenance Hours/Sem (peak and non peak) | 760
Total Cost | 4760
Bagging + Booking System
Total Cost | 6760
Manhour Cost saved with New System/Sem | 1240 | From the graph, the breakeven point is oberseved after 3 semesters.

## Control Plan
Control Plan
Green Box - Uncertainty
Blue Box - Decision

## Meeting Minutes
| Date of Meeting | Location | Nature of Meeting | Attachment (Double Click Icon to Open)
1. | 2015-01-14 | SMU Library, Project Room 4-2 | Kick-Off Meeting
2. | 2015-01-21 | SMU Library, Project Room 4-2 | Project Charter Refinement and KJ Analysis
3. | 2015-01-28 | SMUX, Huddle Room 1 | Review with Prof Adel
4. | 2015-02-04 | SMU Library, Project Room 4-2 | C&E Matrix and Data Collection Discussion
5. | Wednesday, 11 February 2015 | SMU Library, Project Room 4-2 | C&E Matrix and Data Collection Discussion | ..\Meeting Minutes\11 February Meeeting for data collection.doc
6. | Monday, 16 February 2015 | SMUX, Meeting Room 2 | C&E Matrix and FMEA
7. | Wednesday, 25 February 2015 | SMU Library, Study Booth 1 | FMEA, MSA and Pugh Concept Selection Matrix
8. | 2015-03-04 | SMU Library. Project Room 4-7 | MSA, Pugh Concept Selection Matrix
9. | 2015-03-09 | SMU Library. Project Room 4-3 | Data Collection Analysis
10. | 2015-03-11 | SMU Library Office. Meeting Room 3.1 | DOE Discussion
11. | Wednesday, 25 March 2015 | SMU Library. Project Room 3.2 | Fishbone, Process Control
12. | Tuesday, 31 March 2015 | SOB Seminar Room 2.5 | DOE Consultation
13. | 2015-04-01 | SMU Library, Project Room 3-5 | DOE Results and Discussion
14. | 2015-04-07 | SMU Library, Project Room 4-1 | DOE 1 Feedback , DOE 2, Project Control Plan, Poster
15. | Saturday, 18 April 2015 | SOA GSR 3-6 | Poster presentation preparation

## Timeline
| W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Define | W2: Charter + Schedule; W3: KJ; W4: Define Gate
Measure | W0: data collection; W3: process observation; W4: Y; W5: X; W6: X; W7: X; W8: Measure Gate; W9: X; W10: X
| data description |  |  |  | (MSA) | Descriptive Stats | SPC | Process Capability
Analyze | W0: qualitative; W4: Process Mapping; W5: C&E; W7: FMEA; W8: FMEA
| quantitative |  |  |  |  | Descriptive Stats |  |  | hypothesis testing | multi-vari analysis | multi-vari analysis | Analyze Gate
Improve | W5: Best Practice Research; W8: Typical Improvements; W9: Solution Proposals; W10: Solution Proposals; W11: Pugh Matrix; W12: Experiments; W13: Experiments; W14: Improve Gate
Control | W14: Document new process + train; W15: Poster Presentation; W16: Control Gate